## Start Here
NP CONNECT ¦ MARKETING TOOLKIT
Project Timeline & Event Planner
Looking to organize a large website or event project? This Excel template will help you define specific tasks and create timelines. Easy to use and make your own.
Big projects don't fail because of one huge mistake. They fail because of 40 small tasks nobody owned. This workbook gives every task an owner and a date, draws the timeline for you, and yells (politely, in red) when something's late.
WHAT'S INSIDE
■ | Overview: every project on one page with % complete, overdue tasks, next deadline and health.
■ | Project Brief: the 10-minute kickoff that saves 10 meetings. Goal, scope, who decides, risks.
■ | Website Project: a full website build plan, a page tracker and a 20-point launch checklist.
■ | Digital Campaign: ad campaigns, launches and promos, plus an asset tracker.
■ | Trade Show & Event: a countdown plan from 5 months out to follow-up, who you want to meet, the event budget, results, packing list, staff schedule, follow-up plan and show notes.
■ | Event Calendar & Budget: every event for the year with costs, leads, revenue, return on spend and "go again?"
■ | Event ROI Calculator: should you do the show? Worst, expected and best case, plus break-even.
■ | Other Project: a blank plan for everything else. AI & Tools: prompts and the tools that pair with this workbook.
HOW THE TIMELINES WORK
1. Type the kickoff date (or event date) at the top of a project tab. Every task's start date counts from it, so change one date and the whole plan moves.
2. For each task: owner, start offset (days from the kickoff, or negative days before an event), how many days it takes, and which task it depends on.
3. Need a task locked to a specific date? Type it in "Fixed start" and it ignores the offset.
4. Update Status and % done every week. The bars, flags and the Overview update on their own.
THE COLOR CODE
Green cells with blue text = you type here. White cells = formulas. Leave them alone and they'll do the math.
This file comes loaded with SAMPLE projects so you can see how it works. The sample dates are tied to today's date, so the demo always looks current. Type your real kickoff and event dates to make it yours, then replace the tasks.
PICKLE POINT
"If it's documented, it's scalable... and frees you up to sell." Nick Packard
More free tools from the book Picklefarts: Stupid Ideas. Smart Marketing. at nickisatool.com

## Overview
Project Overview
Every project in this workbook on one page. All calculated.
Today: Wednesday, October 14, 2026
Tab | Project | Lead | Starts | Finishes | % complete | Tasks | Done | Overdue | Next deadline | Health
Website Project | Website refresh | Owner | 2026-09-09 | 2026-12-13 | 51.42% | 23 | 6 | 1 | 2026-10-15 | Needs attention
Digital Campaign | Fall offer campaign | Marcus | 2026-10-04 | 2026-11-25 | 15.81% | 13 | 3 | 0 | 2026-10-19 | On track
Trade Show & Event | Spring Home & Builder Expo | Owner | 2026-09-14 | 2027-03-08 | 8.763% | 24 | 5 | 0 | 2026-10-28 | On track
Other Project | [Project name] | [Project lead] | 2026-10-28 | 2026-12-04 | 0% | 10 | 0 | 0 | 2026-10-29 | Not started
Need more projects? Right-click a project tab > Move or Copy > Create a copy. Then add a row here and point it at the new tab.
EVENTS THIS YEAR (from the Event Calendar & Budget tab)
Events on the calendar |  | 7
Total estimated event spend |  | 18350
Actual spent so far |  | 7950
Leads from events |  | 79
Revenue from events |  | 33000
Cost per lead (events) |  | 100.6329

## Project Brief
Project Brief
Fill this out before anyone touches a task. Ten minutes here saves ten meetings later. Make a copy of this tab for each project.
THE BASICS
Project name | Website refresh
Project lead (one name) | Owner
Kickoff + deadline | Kickoff in early September, launch before the holiday rush
Budget | $12,000 (includes agency, photos and plugins)
WHY ARE WE DOING THIS?
The problem | Our site is 6 years old, slow on phones, and doesn't explain what we do. Leads from the site dropped 30% this year.
What success looks like (with numbers) | Double website leads within 6 months. Page speed score over 80 on mobile. Owner can update content without calling anyone.
How we'll measure it | GA4 key events, form fills in the CRM, PageSpeed Insights before and after (Marketing KPI Tracker).
SCOPE
In scope | New design, 12 pages, copy rewrite, photos, SEO basics, forms connected to the CRM, redirects.
Out of scope (just as important) | Ecommerce, a customer portal, the blog backlog. Parked for phase 2.
WHO'S INVOLVED
Decides (one person) | Owner
Does the work | Agency (design + build), Jess (copy + photos)
Gets a say before decisions | Marcus (sales), our top 3 customers (quick feedback)
Gets updates | Whole team, every Friday
RISKS (and what we'll do about them)
Risk | How likely? | How bad? | Our plan
Copy takes forever (it always does) | High | High | AI drafts first, one approver, 48-hour turnaround
Photos aren't ready | Medium | Medium | Book the photographer in week 2
Scope creep | High | High | New ideas go to the phase 2 list, not this project
HOW WE'LL COMMUNICATE
Weekly update (day + time) | Fridays by noon, 5 bullets: done, next, stuck, decisions needed, risks
Where tasks and files live | This workbook + shared Google Drive folder (01 Brief, 02 Content, 03 Design, 04 Final)
Meetings | 15-minute check-in every Tuesday. That's it.
SIGN-OFF
Approved by + date

## Website Project
Website Project
A website build or refresh, start to finish. Change the kickoff date and the whole timeline moves.
| Project name | Website refresh |  |  | % complete | 51.42% |  |  | Tasks done | 6 of 23
| Project lead | Owner |  |  | Starts | 2026-09-09 |  |  | Overdue tasks | 1
| Kickoff date | 2026-09-09 |  |  | Finishes | 2026-12-13 |  |  | Next deadline | 2026-10-15
| Budget | 12000
| Goal | Double website leads within 6 months of launch
Sample uses today's date so the demo always looks live. Type your real date here and every task moves with it.
|  | Offsets count from the kickoff date. | [11 empty] | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar
# | Phase | Task | Owner | Start offset (days) | Fixed start (optional) | Start | Days | End | Depends on # | Status | % done | Flag | Notes | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29
1 | Discovery | Kickoff meeting + project brief (Project Brief tab) | Owner | 0 |  | 2026-09-09 | 2 | 2026-09-10 |  | Done | 100%
2 | Discovery | Goals, audience and success metrics (use your Target Client Profile) | Owner | 2 |  | 2026-09-11 | 5 | 2026-09-15 | 1 | Done | 100%
3 | Discovery | Site audit + analytics baseline (GA4, Search Console) | Agency | 2 |  | 2026-09-11 | 7 | 2026-09-17 | 1 | Done | 100%
4 | Discovery | Sitemap + page list (Page Tracker below) | Agency | 9 |  | 2026-09-18 | 5 | 2026-09-22 | 3 | Done | 100%
5 | Discovery | Content plan: who writes what, and by when | Jess | 12 |  | 2026-09-21 | 4 | 2026-09-24 |  | In progress | 80% | Overdue
6 | Design | Wireframes: home + key pages | Agency | 16 |  | 2026-09-25 | 7 | 2026-10-01 | 4 | Done | 100%
7 | Design | Design mockups | Agency | 23 |  | 2026-10-02 | 10 | 2026-10-11 | 6 | Done | 100%
8 | Design | Design review + approval | Owner | 33 |  | 2026-10-12 | 4 | 2026-10-15 | 7 | Waiting on someone | 50%
9 | Content | Write page copy (AI drafts, humans finish) | Jess | 16 |  | 2026-09-25 | 21 | 2026-10-15 | 5 | In progress | 90%
10 | Content | Collect and edit photos and video | Jess | 20 |  | 2026-09-29 | 21 | 2026-10-19 | 5 | In progress | 70%
11 | Content | SEO: keywords, title tags, meta descriptions | Agency | 30 |  | 2026-10-09 | 7 | 2026-10-15 |  | In progress | 70%
12 | Content | Copy review + approval | Owner | 37 |  | 2026-10-16 | 5 | 2026-10-20 | 9 | Not started
13 | Build | Build theme + page templates | Agency | 37 |  | 2026-10-16 | 14 | 2026-10-29 | 8 | Not started
14 | Build | Load content + images | Agency | 51 |  | 2026-10-30 | 7 | 2026-11-05 | 13 | Not started
15 | Build | Forms, CRM and email integrations | Agency | 51 |  | 2026-10-30 | 5 | 2026-11-03 | 13 | Not started
16 | Build | 301 redirects from every old URL | Agency | 56 |  | 2026-11-04 | 3 | 2026-11-06 | 4 | Not started
17 | Launch | QA: mobile, browsers, speed, forms, links (checklist below) | Agency | 58 |  | 2026-11-06 | 5 | 2026-11-10 | 14 | Not started
18 | Launch | Accessibility + privacy check | Agency | 60 |  | 2026-11-08 | 3 | 2026-11-10 | 14 | Not started
19 | Launch | Final approval | Owner | 63 |  | 2026-11-11 | 2 | 2026-11-12 | 17 | Not started
20 | Launch | Go live (and tell everyone) | Agency | 65 |  | 2026-11-13 | 1 | 2026-11-13 | 19 | Not started
21 | After launch | Submit sitemap + confirm tracking works | Agency | 66 |  | 2026-11-14 | 2 | 2026-11-15 | 20 | Not started
22 | After launch | Fix-it list (first 2 weeks) | Agency | 66 |  | 2026-11-14 | 14 | 2026-11-27 | 20 | Not started
23 | After launch | 30-day results review | Owner | 95 |  | 2026-12-13 | 1 | 2026-12-13 | 20 | Not started
Bar colors: green = scheduled, gray = done, red = overdue, gold = waiting or blocked, yellow column = this week. "Check order" means a task starts before the task it depends on ends.
PAGE TRACKER
| Page |  | Copy | Images | Design | Built | SEO | Approved | % done
| Home |  | Done | Done | Done | In progress | In progress | Not started | 50%
| About |  | Done | In progress | Done | Not started | Not started | Not started | 33.33%
| Services (main) |  | In progress | In progress | Done | Not started | Not started | Not started | 16.67%
| Service page: [name] |  | In progress | Not started | In progress | Not started | Not started | Not started | 0%
| Reviews / case studies |  | Not started | Not started | In progress | Not started | Not started | Not started | 0%
| Contact / book a call |  | Done | Done | Done | Not started | Not started | Not started | 50%
| Blog |  | Not started | Not started | Not started | Not started | Not started | Not started | 0%
| Privacy policy |  | In progress | Not started | Not started | Not started | Not started | Not started | 0%
LAUNCH CHECKLIST (don't skip this... seriously)
| Check |  | Done? | Owner | Notes
| Looks right on phones and tablets |  | No | Agency
| Works in Chrome, Safari, Edge and Firefox |  | No | Agency
| Page speed checked (Google PageSpeed Insights) |  | No | Agency
| Every form tested and lands in the right inbox or CRM |  | No | Agency
| Thank-you pages and conversions tracking in GA4 |  | No | Agency
| GA4 and Google Tag Manager installed |  | No | Agency
| Search Console verified and sitemap submitted |  | No | Agency
| 301 redirects working for every old URL |  | No | Agency
| Title tags and meta descriptions on every page |  | No | Agency
| Alt text on every image |  | No | Agency
| HTTPS everywhere (no security warnings) |  | No | Agency
| Favicon and social share image (1200 x 630) |  | No | Agency
| Privacy policy and cookie notice (where required) |  | No | Agency
| Accessibility basics: contrast, headings, keyboard navigation |  | No | Agency
| Custom 404 page |  | No | Agency
| Phone number tap-to-call on mobile |  | No | Agency
| Google Business Profile website link updated |  | No | Jess
| Backups scheduled |  | No | Agency
| Plugins and theme updated, admin logins use 2-factor |  | No | Agency
| WordPress: "Discourage search engines" turned OFF |  | No | Agency
| Ready to launch? |  | Not yet: 20 left

## Digital Campaign
Digital Campaign
Ad campaigns, product launches, promos and email pushes. Change the kickoff date and everything moves.
| Project name | Fall offer campaign |  |  | % complete | 15.81% |  |  | Tasks done | 3 of 13
| Project lead | Marcus |  |  | Starts | 2026-10-04 |  |  | Overdue tasks | 0
| Kickoff date | 2026-10-04 |  |  | Finishes | 2026-11-25 |  |  | Next deadline | 2026-10-19
| Budget | 6000
| Goal | 60 booked calls at under $100 each
Sample uses today's date so the demo always looks live. Type your real date here and every task moves with it.
|  | Offsets count from the kickoff date. | [11 empty] | Sep | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr
# | Phase | Task | Owner | Start offset (days) | Fixed start (optional) | Start | Days | End | Depends on # | Status | % done | Flag | Notes | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19
1 | Strategy | Campaign brief: goal, audience, offer, budget | Owner | 0 |  | 2026-10-04 | 3 | 2026-10-06 |  | Done | 100%
2 | Strategy | Audience + message (pull from your Target Client Profile) | Marcus | 3 |  | 2026-10-07 | 3 | 2026-10-09 | 1 | Done | 100%
3 | Strategy | Offer + landing page plan | Marcus | 5 |  | 2026-10-09 | 4 | 2026-10-12 | 2 | Done | 100%
4 | Build | Landing page copy + design | Agency | 9 |  | 2026-10-13 | 7 | 2026-10-19 | 3 | In progress | 10%
5 | Build | Ad creative: images + short video | Jess | 9 |  | 2026-10-13 | 10 | 2026-10-22 | 3 | In progress | 10%
6 | Build | Ad copy variations (let AI draft 10, keep 3) | Jess | 12 |  | 2026-10-16 | 4 | 2026-10-19 | 3 | Not started
7 | Build | Email sequence (3 emails) | Jess | 14 |  | 2026-10-18 | 5 | 2026-10-22 | 3 | Not started
8 | Build | Tracking: UTM links, pixels, GA4 conversions | Agency | 16 |  | 2026-10-20 | 3 | 2026-10-22 | 4 | Not started
9 | Launch | QA everything (links, forms, tracking, mobile) | Marcus | 19 |  | 2026-10-23 | 2 | 2026-10-24 | 8 | Not started
10 | Launch | Launch ads + emails | Agency | 21 |  | 2026-10-25 | 1 | 2026-10-25 | 9 | Not started
11 | Optimize | Weekly optimization: kill losers, scale winners | Agency | 22 |  | 2026-10-26 | 28 | 2026-11-22 | 10 | Not started
12 | Optimize | Mid-campaign check-in | Owner | 35 |  | 2026-11-08 | 1 | 2026-11-08 | 10 | Not started
13 | Wrap-up | Final report + what we'd do differently | Marcus | 50 |  | 2026-11-23 | 3 | 2026-11-25 | 11 | Not started
Bar colors: green = scheduled, gray = done, red = overdue, gold = waiting or blocked, yellow column = this week. "Check order" means a task starts before the task it depends on ends.
ASSET TRACKER
| Asset |  | Channel | Size / spec | Owner | Due | Status | Link to file
| Landing page |  | Website | Desktop + mobile | Agency | 2026-10-20 | In progress
| Facebook / Instagram feed ad (3 versions) |  | Meta | 1080 x 1350 | Jess | 2026-10-22 | Not started
| Reel / Story ad |  | Meta | 1080 x 1920, 15 sec | Jess | 2026-10-22 | Not started
| LinkedIn single image ad |  | LinkedIn | 1200 x 627 | Jess | 2026-10-22 | Not started
| Google search ads (headlines + descriptions) |  | Google | 15 headlines, 4 descriptions | Agency | 2026-10-22 | Not started
| Email 1: the offer |  | Email | Plain text + 1 image | Jess | 2026-10-23 | Not started
| Email 2: proof |  | Email |  | Jess | 2026-10-23 | Not started
| Email 3: last call |  | Email |  | Jess | 2026-10-23 | Not started
Due dates on the sample assets follow the kickoff date. Type over them with real dates whenever you like.

## Trade Show & Event
Trade Show & Event
Plan a show by counting back from the event date. Change the date and every task moves with it.
| Project name | Spring Home & Builder Expo |  |  | % complete | 8.763% |  |  | Tasks done | 5 of 24
| Project lead | Owner |  |  | Starts | 2026-09-14 |  |  | Overdue tasks | 0
| Event date | 2027-02-11 |  |  | Finishes | 2027-03-08 |  |  | Next deadline | 2026-10-28
| Budget | 9500
| Goal | 40 qualified leads, 12 meetings, 3 new customers
Sample uses today's date so the demo always looks live. Type your real date here and every task moves with it.
|  | Offsets count from the event date (negative = before the event). | [11 empty] | Sep |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr
# | Phase | Task | Owner | Start offset (days) | Fixed start (optional) | Start | Days | End | Depends on # | Status | % done | Flag | Notes | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05
1 | 4+ months out | Pick the show and set goals: leads, meetings, sales | Owner | -150 |  | 2026-09-14 | 7 | 2026-09-20 |  | Done | 100%
2 | 4+ months out | Run the numbers on the Event ROI Calculator. Go or no-go? | Owner | -145 |  | 2026-09-19 | 2 | 2026-09-20 |  | Done | 100%
3 | 4+ months out | Book booth space + read the exhibitor manual (deadlines!) | Owner | -140 |  | 2026-09-24 | 3 | 2026-09-26 | 2 | Done | 100%
4 | 4+ months out | Set the event budget (below) | Owner | -138 |  | 2026-09-26 | 3 | 2026-09-28 | 3 | Done | 100%
5 | 4+ months out | Book hotel + travel | Marcus | -130 |  | 2026-10-04 | 2 | 2026-10-05 | 3 | Done | 100%
6 | 3 months out | Booth design + graphics brief | Jess | -112 |  | 2026-10-22 | 7 | 2026-10-28 | 3 | Not started
7 | 3 months out | Plan the hook: the demo, game or stunt that stops people | Owner | -105 |  | 2026-10-29 | 10 | 2026-11-07 | 6 | Not started
8 | 3 months out | Order booth, banners and signage | Jess | -100 |  | 2026-11-03 | 5 | 2026-11-07 | 6 | Not started
9 | 3 months out | Lead capture setup (scanner app, form or CRM) | Marcus | -90 |  | 2026-11-13 | 5 | 2026-11-17 |  | Not started
10 | 2 months out | Order giveaways (only if they tie to your message) | Jess | -60 |  | 2026-12-13 | 5 | 2026-12-17 | 7 | Not started
11 | 2 months out | Pre-show outreach: email + LinkedIn to attendees | Marcus | -56 |  | 2026-12-17 | 28 | 2027-01-13 | 9 | Not started
12 | 2 months out | Book meetings with top prospects | Marcus | -42 |  | 2026-12-31 | 35 | 2027-02-03 |  | Not started
13 | 1 month out | Print sales docs + business cards | Jess | -35 |  | 2027-01-07 | 7 | 2027-01-13 |  | Not started
14 | 1 month out | Social posts: "Come see us at booth #___" | Jess | -30 |  | 2027-01-12 | 28 | 2027-02-08 |  | Not started
15 | 2 weeks out | Staff schedule + booth training (the 30-second pitch) | Owner | -14 |  | 2027-01-28 | 7 | 2027-02-03 |  | Not started
16 | 2 weeks out | Ship booth + materials (check the shipping deadline) | Marcus | -12 |  | 2027-01-30 | 3 | 2027-02-01 | 8 | Not started
17 | 2 weeks out | Pack the kit (packing list below) | Jess | -5 |  | 2027-02-06 | 3 | 2027-02-08 |  | Not started
18 | Show | Setup day | Team | -1 |  | 2027-02-10 | 1 | 2027-02-10 | 16 | Not started
19 | Show | Show days: work the booth | Team | 0 |  | 2027-02-11 | 3 | 2027-02-13 | 18 | Not started
20 | Show | Upload leads + notes every night | Marcus | 0 |  | 2027-02-11 | 3 | 2027-02-13 | 9 | Not started
21 | After | Teardown + ship back | Team | 3 |  | 2027-02-14 | 1 | 2027-02-14 | 19 | Not started
22 | After | Follow up with every lead within 48 hours | Marcus | 3 |  | 2027-02-14 | 2 | 2027-02-15 | 20 | Not started
23 | After | Hot leads into the sales cadence (Multi-Touch Sales Script) | Marcus | 5 |  | 2027-02-16 | 21 | 2027-03-08 | 22 | Not started
24 | After | Results recap: cost per lead, meetings, pipeline. Go again? | Owner | 14 |  | 2027-02-25 | 3 | 2027-02-27 | 22 | Not started
Bar colors: green = scheduled, gray = done, red = overdue, gold = waiting or blocked, black = event week, yellow column = this week. "Check order" means a task starts before the task it depends on ends.
WHO WE WANT TO MEET (pull from your Target Client Profile)
| Audience bucket | Who they are |  | What they care about |  |  |  | Our hook / message |  |  |  | Goal
| Builders + remodelers | Owners and project managers at small to mid-size builders |  | Reliable subs who show up on schedule |  |  |  | "We hit your schedule or the install is free." |  |  |  | 15 conversations
| Homeowners planning projects | Homeowners 35 to 65 with a project in the next year |  | Not getting ripped off, comfort, energy bills |  |  |  | "Free comfort check: find out what your house actually needs." |  |  |  | 25 leads
| Property managers | Managers of 20+ units |  | Fast response, one vendor for everything |  |  |  | "One call. Every unit. Same-week service." |  |  |  | 5 meetings
EVENT BUDGET
| Category | Item | Estimated |  | Actual |  | Notes
| Booth & rentals | Booth space | 3500 |  | 3500
| Booth & rentals | Electricity, internet, furniture, carpet | 600
| Booth & rentals | Booth display + graphics | 1800 |  | 1650
| Promotion | Pre-show ads (search + social) | 600
| Promotion | Email + direct mail to attendees | 400
| Promotion | Sponsorship add-ons (show guide ad, banner) | 500
| Swag & handouts | Booth game or demo | 300
| Swag & handouts | Sales docs + business cards | 250
| Swag & handouts | Giveaways / gift cards | 400
| Travel & shipping | Shipping + drayage | 450
| Travel & shipping | Hotel + travel | 500
| Travel & shipping | Meals | 200
| Other | Lead capture app | 0
|  | Total | 9500 |  | 5150 |  | Right on budget
RESULTS (fill in after the show)
|  | Leads collected |  |  | Cost per lead
|  | Qualified leads |  |  | Cost per meeting
|  | Meetings booked |  |  | Return on spend (revenue)
|  | New customers (so far) |  |  | Go again next year?
Revenue from those customers
Costs use your actual total once you enter it, otherwise the estimate. Log the totals on the Event Calendar & Budget tab too.
| PACKING LIST | [6 empty] | BOOTH STAFF SCHEDULE
| Item |  | Qty | Packed? | Notes |  |  | Day | Time | Who |  | Role
| Booth display + graphics |  | 1 | No |  |  |  | Day 1 | 8:00-12:00 | Owner | Greeter + demo
| Table cover / tablecloth |  | 1 | No |  |  |  | Day 1 | 12:00-5:00 | Marcus | Meetings + lead capture
| Banner stands |  | 2 | No |  |  |  | Day 2 | 8:00-12:00 | Jess | Greeter + social posts
| Monitor or tablet + stand (for the demo) |  | 1 | No |  |  |  | Day 2 | 12:00-5:00 | Owner | Meetings
| Extension cords + power strip |  | 2 | No |  |  |  | Day 3 | 8:00-12:00 | Marcus | Greeter + lead capture
| Phone chargers + battery packs |  | 3 | No |  |  |  | Day 3 | 12:00-3:00 | Team | Last push + teardown
| Lead capture device or app login |  | 1 | No
| Business cards |  | 500 | No
| Sales docs / one-pagers |  | 200 | No
| Giveaways |  | 300 | No
| Bowl or game for the hook |  | 1 | No
| Pens + sharpies |  | 10 | No |  |  |  | LEAD FOLLOW-UP PLAN
| Tape, zip ties, scissors, box cutter |  | 1 | No |  |  |  | Hot | Call within 24 hours + email recap
| Cleaning wipes + trash bags |  | 1 | No |  |  |  | Warm | Email within 48 hours + LinkedIn invite
| Water + snacks |  | 1 | No |  |  |  | Cold | Add to newsletter (with permission)
| Comfortable shoes (trust me) |  | 1 | No |  |  |  | Everyone | Thank-you note referencing your conversation
| Branded shirts |  | 4 | No
| Exhibitor manual + shipping labels |  | 1 | No
| First aid kit + mints |  | 1 | No
| Return shipping labels |  | 1 | No
| Still to pack: |  | 20
SHOW NOTES
Note (what worked, what didn't, who we met, ideas for next year)

## Event Calendar & Budget
Event Calendar & Budget
Every show, sponsorship and event for the year in one list: what it costs, what it brought in, and whether it's worth doing again.
Return on spend = (revenue - cost) ÷ cost. Uses actual spend when you have it, otherwise the estimate. Revenue takes time to show up after events, so update it every quarter.
Event | Website | Start date | Type | Status | Booth & rentals | Promotion | Swag & handouts | Travel & other | Total estimated | Actual spent | Leads | Meetings | New customers | Revenue | Cost per lead | Return on spend | Go again? | Notes
Chamber annual expo | https:// | 2026-02-12 | Trade show | Done | 1200 | 300 | 200 | 100 | 1800 | 1650 | 22 | 6 | 2 | 9500 | 75 | 475.8% | Yes | Great local turnout
Spring Home & Builder Expo | https:// | 2027-03-18 | Trade show | Booked | 5900 | 1500 | 950 | 1150 | 9500 | [8 empty] | See the Trade Show & Event tab
Industry association conference | https:// | 2026-05-06 | Trade show | Done | 2500 | 400 | 300 | 900 | 4100 | 4300 | 18 | 4 | 1 | 6000 | 238.8889 | 39.53% | Maybe (with changes) | Booth location was bad. Ask for a corner.
Golf outing sponsorship | https:// | 2026-06-20 | Sponsorship | Done | 750 | 0 | 400 | 150 | 1300 | 1300 | 9 | 5 | 2 | 14000 | 144.4444 | 976.9% | Yes | Relationships > booth. Play, don't sell.
Neighborhood fall festival | https:// | 2026-09-26 | Community | Done | 300 | 100 | 250 | 0 | 650 | 700 | 30 | 2 | 1 | 3500 | 23.3333 | 400% | Yes | Kids game was the hook
Lunch-and-learn workshop (hosted) | https:// | 2026-11-12 | Hosted event | Planned | 0 | 300 | 100 | 400 | 800 | [8 empty] | Teach one thing really well
Holiday networking mixer | https:// | 2026-12-04 | Networking | Considering | 150 | 0 | 0 | 50 | 200
Totals |  |  |  |  | 10800 | 2600 | 2200 | 2750 | 18350 | 7950 | 79 | 17 | 6 | 33000 | 100.6329
ESTIMATED EVENT SPEND BY MONTH
Month | Year: | 2026
|  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | Total
Estimated spend |  | 0 | 1800 | 0 | 0 | 4100 | 1300 | 0 | 0 | 650 | 0 | 800 | 200 | 8850
Events |  | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1
Feeding the Marketing Schedule & Budget template? Copy each event's total into your Campaign Calendar with the Events & sponsorships category.
Formulas:
Start date = SUMIFS(J6:J30,C6:C30,">="&[Start date, row above],C6:C30,"<="&EOMONTH([Start date, row above],0))
Type = SUMIFS(J6:J30,C6:C30,">="&[Type, row above],C6:C30,"<="&EOMONTH([Type, row above],0))
Status = SUMIFS(J6:J30,C6:C30,">="&[Status, row above],C6:C30,"<="&EOMONTH([Status, row above],0))
Booth & rentals = SUMIFS(J6:J30,C6:C30,">="&[Booth & rentals, row above],C6:C30,"<="&EOMONTH([Booth & rentals, row above],0))
Promotion = SUMIFS(J6:J30,C6:C30,">="&[Promotion, row above],C6:C30,"<="&EOMONTH([Promotion, row above],0))
Swag & handouts = SUMIFS(J6:J30,C6:C30,">="&[Swag & handouts, row above],C6:C30,"<="&EOMONTH([Swag & handouts, row above],0))
Travel & other = SUMIFS(J6:J30,C6:C30,">="&[Travel & other, row above],C6:C30,"<="&EOMONTH([Travel & other, row above],0))
Total estimated = SUMIFS(J6:J30,C6:C30,">="&[Total estimated, row above],C6:C30,"<="&EOMONTH([Total estimated, row above],0))
Actual spent = SUMIFS(J6:J30,C6:C30,">="&[Actual spent, row above],C6:C30,"<="&EOMONTH([Actual spent, row above],0))
Leads = SUMIFS(J6:J30,C6:C30,">="&[Leads, row above],C6:C30,"<="&EOMONTH([Leads, row above],0))
Meetings = SUMIFS(J6:J30,C6:C30,">="&[Meetings, row above],C6:C30,"<="&EOMONTH([Meetings, row above],0))
New customers = SUMIFS(J6:J30,C6:C30,">="&[New customers, row above],C6:C30,"<="&EOMONTH([New customers, row above],0))

## Event ROI Calculator
Event ROI Calculator
Should we do this show? Run the numbers before you sign the booth contract.
WHAT A CUSTOMER IS WORTH
Average monthly value of a customer | 500 |  | What a typical customer pays you per month (or yearly value ÷ 12).
Average length of the relationship (months) | 24
Lifetime value of a customer | 12000
Gross margin | 45% |  | What you keep after the cost of delivering the work. Judge events on profit, not just revenue.
Lifetime profit from a customer | 5400
THE EVENT
Total event cost | 9500 |  | Booth, promotion, swag, travel, shipping. The Trade Show & Event tab budget adds this up for you.
Pull total from the Trade Show & Event tab instead? | No
Cost used below | 9500
SCENARIOS
| Worst case | Expected | Best case
Leads collected | 20 | 40 | 60
Lead-to-customer rate | 5% | 8% | 12%
New customers | 1 | 3.2 | 7.2
First-year revenue | 6000 | 19200 | 43200
Lifetime revenue | 12000 | 38400 | 86400
Lifetime profit | 5400 | 17280 | 38880
Cost per lead | 475 | 237.5 | 158.3333
Cost per new customer | 9500 | 2968.75 | 1319.4444
ROI (lifetime profit vs. cost) | -43.16% | 81.89% | 309.3%
BREAK-EVEN
Customers you need to break even | 1.8
Leads you need (at the expected close rate) | 22
The verdict | Probably go, if you can hit the expected numbers. Plan your hook and pre-show outreach.
Lifetime numbers take time to show up. Track the real results on the Event Calendar & Budget tab and check back in 6 to 12 months.

## Other Project
Other Project
For everything else: office moves, new service launches, rebrands, hiring pushes. Rename the phases and tasks to fit.
| Project name | [Project name] |  |  | % complete | 0% |  |  | Tasks done | 0 of 10
| Project lead | [Project lead] |  |  | Starts | 2026-10-28 |  |  | Overdue tasks | 0
| Kickoff date | 2026-10-28 |  |  | Finishes | 2026-12-04 |  |  | Next deadline | 2026-10-29
| Budget | 0
| Goal | [What does success look like?]
Sample uses today's date so the demo always looks live. Type your real date here and every task moves with it.
|  | Offsets count from the kickoff date. | [11 empty] | Oct | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May
# | Phase | Task | Owner | Start offset (days) | Fixed start (optional) | Start | Days | End | Depends on # | Status | % done | Flag | Notes | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17
1 | Plan | Define the goal and what "done" looks like (Project Brief) | Owner | 0 |  | 2026-10-28 | 2 | 2026-10-29 |  | Not started
2 | Plan | List every task (use the AI prompt on the AI & Tools tab) | Owner | 2 |  | 2026-10-30 | 2 | 2026-10-31 | 1 | Not started
3 | Plan | Assign owners, days and dependencies | Owner | 4 |  | 2026-11-01 | 1 | 2026-11-01 | 2 | Not started
4 | Do | Phase 1: [name it] | [Owner] | 5 |  | 2026-11-02 | 10 | 2026-11-11 | 3 | Not started
5 | Do | Phase 2: [name it] | [Owner] | 12 |  | 2026-11-09 | 10 | 2026-11-18 |  | Not started
6 | Do | Weekly check-in (15 minutes, same day every week) | Owner | 5 |  | 2026-11-02 | 30 | 2026-12-01 | 3 | Not started
7 | Review | Review + feedback | Owner | 22 |  | 2026-11-19 | 4 | 2026-11-22 | 5 | Not started
8 | Review | Final changes | [Owner] | 26 |  | 2026-11-23 | 3 | 2026-11-25 | 7 | Not started
9 | Launch | Launch / deliver | [Owner] | 30 |  | 2026-11-27 | 1 | 2026-11-27 | 8 | Not started
10 | Wrap-up | Wrap-up: what worked, what didn't, what we'd change | Owner | 37 |  | 2026-12-04 | 1 | 2026-12-04 | 9 | Not started
Bar colors: green = scheduled, gray = done, red = overdue, gold = waiting or blocked, yellow column = this week. "Check order" means a task starts before the task it depends on ends.

## AI & Tools
AI & Tools
Let AI build the first draft of your plan, then let the right tools keep everyone on track.
Use it to... | Prompt (copy and paste into Claude, ChatGPT, Gemini or Copilot) | Pro tip
Build the task list | Act as an experienced project manager. I'm planning a [website build / trade show / campaign / other] for [business]. Goal: [goal]. Deadline: [date]. Team: [names and roles]. Budget: [$]. Give me every task, grouped by phase, with an owner role, a realistic number of days, and which task each one depends on. Format it as a table with columns: Phase, Task, Owner, Start offset (days from kickoff), Days, Depends on #. | Paste the table straight into a project tab. Then cut anything that doesn't matter.
Sanity-check the timeline | Here's my project plan: [paste]. What did I forget? Where is the timeline unrealistic? Which tasks are most likely to slip, and what should I do now to protect the deadline? | Run this before you share the plan with anyone.
Find the risks | For this project: [describe], list the 10 biggest risks. For each, rate how likely and how bad (low, medium, high) and give one specific thing I can do this week to reduce it. | Copy the top 3 into the Project Brief.
Write the weekly update | Here's this week's task list with statuses: [paste rows]. Write a 5-bullet update for my team and boss: what got done, what's next, what's stuck, decisions I need, and risks. Plain English, no fluff. | Same day, same time, every week. Consistency builds trust.
Turn meeting notes into tasks | Here are my meeting notes: [paste or upload the transcript]. Pull out every action item with an owner and a due date. Flag anything that was discussed but never assigned. | Get permission before you record or use an AI note-taker.
Plan a trade show | I'm exhibiting at [show] on [dates] in [city]. My audience: [who]. Goal: [leads/meetings]. Booth size: [size]. Give me 5 booth hook ideas that stop people walking by, a 30-second pitch for my staff, 3 pre-show email subject lines, and a 48-hour follow-up email. | The hook matters more than the booth. Ask any farting pickle.
Build a website launch checklist | My website runs on [WordPress / Squarespace / Wix / Shopify]. Give me a pre-launch and post-launch checklist specific to that platform: QA, SEO, tracking, redirects, speed, security and accessibility. | Add anything new to the Launch Checklist on the Website tab.
Run a post-mortem | Project: [name]. Planned: [dates, budget, goal]. Actual: [dates, budget, results]. Here's what happened: [notes]. Help me write a post-mortem: what worked, what didn't, root causes, and 5 things we'll do differently next time. | Save it in the Notes or the Show Notes so next year's plan starts smarter.
TOOLS THAT PAIR WITH THIS WORKBOOK
Project boards | Trello, Asana, Monday.com, ClickUp, Microsoft Planner or Notion. Pick one. Not three.
A simple board setup | Lists: Backlog > This Week > Doing > Waiting on Someone > Review > Done. One card per task, one owner per card, a due date on every card.
Files | One shared folder per project: 01 Brief, 02 Content, 03 Design, 04 Final, 05 Results. Link files in the Notes column instead of emailing them.
Communication | One Slack or Teams channel per big project. Decisions get written down there, not in hallway conversations.
Meeting notes | AI note-takers (Zoom AI Companion, Microsoft Teams Copilot, Otter, Fathom) turn calls into task lists. Ask before you record.
Event lead capture | Most shows offer a badge-scanning app. A simple form on a tablet that feeds your CRM works too.
When to graduate from this spreadsheet | More than 3 or 4 people working on it, more than about 75 tasks, or people need reminders and notifications. Use this workbook to plan, then run the day-to-day in a project board.
PICKLE POINT | "If it's documented, it's scalable... and frees you up to sell." Nick Packard